## Introduction
Program Planning and Implementation Workbook
Introduction
This workbook is designed to help support organizations in preparing for implementing a curriculum. It includes tools for recruitment, retention, implementation timelining, fidelity monitoring, quality improvement and sustainability planning. While this is not an exhaustive tool, it can provide the basic planning and monitoring tools needed for program success. Planning and monitoring support programs in delivering high quality services to young people while also focusing on continuous improvement. The ultimate goal of youth programs is to continuously offer programs that improve the lives of youth. To reach this goal, it is critical that we see program implementation planning, delivery, and monitoring as tasks that are just as critical as the way we interact with youth. Taking these tasks seriously allows for additional funding, building partnerships, and improving the quality of services you provide to youth.
How to Use This Workbook
Throughout the workbook, you will find examples and notes that should help you customize this tool for your program. These are provided to get you started and help assist with learning new ways of planning and monitoring youth programs. The workbook and tools are easy to modify and adjust to meet your needs. Though there many other aspects of youth program implementation that you should consider- such as site selection, number of youth you want to implement your program with, curriculum selection, safety and crisis planning, youth engagement and leadership and much more- this workbook is designed to provide the basics to get you started. Following this guide and using the tools in this workbook will help create a stronger program and ensure that your implementation is successful. Note: All sheets are meant to be printed in landscape.
Additional Support
If you need help or support with this workbook or any of the tools within it, please contact Nicole Treviño
Email: info@nicoletrevino.com
Phone: 512-827-7101

## Participant Recruitment
Recruitment Tracking
Broad Outreach
Date | Site | Action | Number of Outreach Contacts | Follow-Up/Tasks | Progress
Ex. 6/15/16 | OutYouth | Dropped off flyers with staff | left 50 flyers,spoke to director | Will set up a time with Director to come back and speak at an event | Complete
Ex. 6/17/16 | HHSC Health Fair | Tabled at Event | 20 youth on sign-in sheet | Follow-up calls with those on sign-in sheets | Complete
Targeted Outreach
Date | Site | Action | Number of Outreach Contacts | Follow-Up/Tasks | Progress
Ex. 6/15/16 | Q | Presentation during event | Presentation to 15 propspective participants; Handed out 30 flyers to promote program; Spoke with 5 interested participants | Follow-up call with interested participants | Complete

## Participant Retention
Retention Tracking
Retention Strategy 1: Example - Incentives
Action Steps | Lead Staff Member | Timeline | Intended Outcomes | Progress/Monitoring
EXAMPLE: Purchase Gift Cards | Zana | 6/15-7/1 | 25, $50 gift cards purchased | Complete as of 6/16
Retention Strategy 2: Example - Engagement
Action Steps | Lead Staff Member | Timeline | Intended Outcomes | Progress/Monitoring
EXAMPLE: Personal calls/texts to youth participants | Jane Doe | 6/15-7/1 | Ensure continued particpation by youth participants | Complete as of 6/16
Retention Strategy 3: Example - Transportation Support
Action Steps | Lead Staff Member | Timeline | Intended Outcomes | Progress/Monitoring
EXAMPLE: Purchase Bus Passes for participants | Jane Doe | 6/15-7/1 | 25 Monthly bus passes purchased | Complete as of 6/16
Retention Strategy 4: __________________
Action Steps | Lead Staff Member | Timeline | Intended Outcomes | Progress/Monitoring
Retention Strategy 5: __________________
Action Steps | Lead Staff Member | Timeline | Intended Outcomes | Progress/Monitoring
Retention Strategy 6: __________________
Action Steps | Lead Staff Member | Timeline | Intended Outcomes | Progress/Monitoring

## Implementation Plan (example)
Implementation Plan Schedule: Site 1
Week | Mon | Tues | Wed | Thurs | Fri
2016-03-07 | Deliever evaluation consent forms.
2016-03-14 | Spring Break- NO CLASSES
2016-03-21 | Distribute evaluation consent forms. |  | Talk with 2A/B and 3A/B about program and consent forms |  | Deadline to pick up consent forms.
2016-03-28 | Baseline survey with participants. | 3/29 - 3/30 SCHOOL TESTING |  | Baseline survey with participants.
2016-04-04 | Implementation Continues- Session 1 in M/W classes | Implementation Continues- Session 1 in T/TH classes | Implementation Continues- Session 2 in M/W classes | Implementation Continues- Session 2 in T/TH classes
2016-04-11 | Implementation Continues- Session 3 in M/W classes | Implementation Continues- Session 3 in T/TH classes | Implementation Continues- Session 4 in M/W classes | Implementation Continues- Session 4 in T/TH classes
2016-04-18 | Implementation Continues- Session 5 in M/W classes | Implementation Continues- Session 5 in T/TH classes | Implementation Continues- Session 6 in M/W classes | Implementation Continues- Session 6 in T/TH classes
2016-04-25 | Implementation Continues- Session 7 in M/W classes | Implementation Continues- Session 7 in T/TH classes | Implementation Continues- Session 8 in M/W classes | Implementation Continues- Session 8 in T/TH classes
2016-05-02 | Implementation Continues- Session 9 in M/W classes | Implementation Continues- Session 9 in T/TH classes | ORGANIZATIONAL TRAINING- Classes may be cancelled
2016-05-09 | SCHOOL TESTING DATES -NO CLASSES
2016-05-16 | Implementation Continues- Session 10 in M/W classes | Implementation Continues- Session 10 in T/TH classes | Post Survey with participants | Post Survey with Participants
2016-05-23 | Focus Group with parents |  | Focus Group with Students
2016-05-30
Note on B1: It may be helpful to plan by each implementation site if you have multiple sites. This allows you to ask each site for dates that you can or cannot do programming to avoid scheduling conflicts.
Note on A4: You can use the date here or week number (e.g. Week 1, Week 2, etc.) Use the method that best fits your needs.
Note on B4: This template can be used to plan for multiple program activities (evaluation, consent collection, baseline surveys, implementation days, and pre/post surveys, follow-up activities, etc.) This also allows you to plug in conflicts, such as testing, community events, or other things that might conflict with your implementation schedule. This template can also be used for separate scheduling efforts. (e.g. recruitment schedule, pre-planning, implementation schedule, evaluation schedule.)
Note on H12: Example of implementation/ programming scheduling.
Note on B22: One example of how conflicts can be represented on the template.
Note on F24: While you can develop separate schedules for different types of activities (programming, evaluation, etc.), if you chose to create one comprehensive plan, also consider color coding to differentiate activity type.

## Implementation Template Site1
[Insert Implementation Site Name] Schedule
Week | Mon | Tues | Wed | Thurs | Fri
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]

## Implementation Template Site2
[Insert Implementation Site Name] Schedule
Week | Mon | Tues | Wed | Thurs | Fri
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]
[INSERT DATE]

## Fidelity Monitoring
Fidelity Monitoring Tool
Core Content Components (include high level lesson outline here):
Did you complete these Core Content Components? | □ Yes, completely □ Yes, with adaptations □ No (please write why in other notes section) | □ Yes, completely □ Yes, with adaptations □ No (please write why in other notes section) | □ Yes, completely □ Yes, with adaptations □ No (please write why in other notes section) | □ Yes, completely □ Yes, with adaptations □ No (please write why in other notes section)
Please indicate adaptations made, if any: | □ Activity Timing □ Instructional Methods □ Content □ Order of Activities □ Cultural Adaptation □ Other: | □ Activity Timing □ Instructional Methods □ Content □ Order of Activities □ Cultural Adaptation □ Other: | □ Activity Timing □ Instructional Methods □ Content □ Order of Activities □ Cultural Adaptation □ Other: | □ Activity Timing □ Instructional Methods □ Content □ Order of Activities □ Cultural Adaptation □ Other:
Please detail adaptations made:
Please describe challenges experienced:
Did your lesson include a Cultural Teaching? | How engaged were youth during this lesson? | Lesson Notes:
(Such as: Poem, Song, Activity)? | □ Very Engaged
□ Yes | □ Somewhat Engaged
□ No | □ Not Engaged

## Quality Improvement Tracker
Quality Improvement Tracker
| Strengths | Challenges | Solutions/Ideas
Program Planning
Ex. Developed Implementation Plan | Plan provides a timeline for our work | We had to work around several school holidays | Next year we'll get dates in advance to support earlier planning
Program Implementation
Ex. Began program implementation at 1 site | We were able to start implementing early which will allow us to finish program before spring break | We still have 2 other sites that will need to be scheduled around spring break | The timeline created for the first site will be used for future years to propose an early start to programming
Curriculum
Ex. Selected a curriculum | We went through a thorough process to select | The selection process took a very long time. | In future selections, we'll start earlier so we don't delay the start of programming
Implementation Site Coordination
Ex. 2 out of 3 sites have been identified and scheduled | Site coordination at 2 sites is really strong | 3rd site is still not identified, the location we wanted to use is not available at the time we want to deliver programming. | Next year, we'll set a criteria for the type of site we want to implement in, such as no gyms or cafeterias since the open space doesn't allow for good discussion.
Partnerships and Contracts
Ex. 2 contract facilitators have been secured | We have 2 facilitators to start programming with | Still looking for a 3rd facilitator, but we are having trouble finding the right person. | We'll look into community members who work well with children and begin the process earlier in the grant year.
Evaluation Activities
Ex. Evaluation tools are finalized | We have pre and post surveys developed for programming as well as consent forms and online tools set up | Our evaluation process and forms are very complicated, parents couldn't make sense of them and they weren't orginally translated into other languages. | Next year we'll color code forms and make it simpler for parents to complete consent forms. We'll also translate forms before sending.
Staff Training and Development
Ex. All but 1 staff has received curriculum training | Most staff are trained on the curriculum and ready to implement. | The 1 staff person who missed training will have to get caught up without formal training. | We'll try to schedule staff training earlier next year and make the training dates mandatory.

## Sustainability Planning
Sustainability Planning
| Progress Made | Resources Needed | Notes
Partnerships
Ex. Implementation Sites | Ex. Secured 2 new schools and 1 community based organization that will partner on implementation after the grant ends | Memorandum of Agreement for new partners
Funding
Ex. Program Donors/ Funding | Ex. Met with 2 foundations and 1 individual donor to provide presentations on the project | Follow up meetings with donors and a handout with program outcomes and needs
Knowledge Management
Ex. Quality Improvement Planning | Ex. Recording lessons learned and outcomes for the project | Integrate lessons learned into next proposal and develop a quality improvement plan.
Staff Retention
Ex. Maintaining Staff | Ex. All 4 facilitators have been retained throughout the course of the first year. | Conduct interviews with each staff to identify their needs and growth opportunities.